## BLANK - Agile Project Plan
Research Planning
| PROJECT NAME | Standard Candles with earth lightbulbs and sat data |  |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
| PROJECT MANAGER | Judol Alejandro Rodríguez Franco |  |  | 2023-08-10 | 2023-11-10 | 10% | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
Yes | SPRINT 1 | Selecting the project | JR |  | 2023-08-10 | 2023-09-07 | 29 | Needs Review
No | Propuestas de Proyecto | Presentación de propuestas de proyecto | JR |  | 2023-08-10 | 2023-08-17 | 8 | Approved
Yes | Planeación de Proyecto | Elección y planeación de proyecto | JR |  | 2023-08-18 | 2023-08-24 | 7 | Complete
Yes | Presentación Proyecto | Presentación del proyecto escogido | JR |  | 2023-08-25 | 2023-09-07 | 14 | Complete
No | SPRINT 2 | Project Execute | JR |  | 2023-09-08 | 2023-10-05 | 28 | In Progress
No | Measurement | Measurement | JR |  | 2023-09-08 | 2023-09-16 | 9 | Not Started
No | Data Analysis | Data Achieve and Analysis | JR |  | 2023-09-17 | 2023-09-28 | 12 | Not Started
No | Results | Results and Expo | JR |  | 2023-09-29 | 2023-10-05 | 7 | Not Started
| SPRINT 3 | Finishing Project | JR |  | 2023-10-06 | 2023-11-09 | 35 | Not Started
No | Prepare Report | Prepare writen doc | JR |  | 2023-10-06 | 2023-10-27 | 22 | Not Started
No | Compile and organize docs | Compile and organize docs | JR |  | 2023-10-28 | 2023-11-03 | 7 | Not Started
No | Final Presentation | Final Presentation | JR |  | 2023-11-04 | 2023-11-09 | 6 | Not Started
Formulas:
START DATE = MIN([START DATE, row below]:G9)
END DATE = MAX([END DATE, row below]:H9)

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold